## Sheet1
Requirements | Description | Application | Assigned to | Impact | DB Changes | File Changes | Effort (hours)
1 | Help Configurations : Need to classify the help menu based on exams. On Page load
User should see the list of exams along with additional type called common with.
| Count for each exam type. on click of a particular exam count that exam specific help | CMS | Prakash |  |  |  | 8
topics should be displayed. Bottom along with help name and description add a
combo box for classifying exam type. Additionally Common which is not existing in
Exam type table should be brought . . For Help Menu also Exam Name and count
should be brought along with common.
2 | Dynamically Forming the Grid (Home Page) based on Exam Type to Section |  |  |  | New Mapping for exam and section using s_exam_section and s_exam_type
Combination, Instead of Fixed Quant and Verbal Combination. A new table to be
created for storing the mappings between the Exam and the Sections. This mapping
| will be done only from DB. No FE Screen is required. Based on the Mapping the grid | Drill | Prithivi Raj |  |  |  | 16
will be populated. Each Section will be like a header at the top, On choosing the
section (like the tab), the corresponding Grid (Levels) will be shown. In short, only
one set of Levels will be displayed, on choosing the Section, By Default the first
Section will be shown in the Screen. Level Banding will color will be as such.
3 | Need to Change the Peer Group query. Quant Level and Verbal Level should be
| referred from the User Exam Level table, instead of User Table, as the Columns | Drill | Prithivi Raj |  |  |  | 24
were removed. And based on a Configuration setup, we will display bring minimal
record. Below we will show a small link or button, Show More. On click of show more
we will display the remaining records.
4 | Pagination to Completed for all the Pages (User Settings, Retry Report, Referral
| Report, Feedback Report, Completion Report, User Properties) in Drill and (Upload | CMS & Drill | Prakash |  |  |  | 8
Status Report, Reviewer Report, Question Status Report) in CMS.
5 | Faculty Report Validations : Change the Multi Select of Exam type to Select Combo
Box during Faculty code generation. And Once a Batch Id is created for a Faculty,
Same Batch ID cannot be used for that Faculty to Generate next set of Codes. We
need to have create a new table just to store the Faculty ID and Batch ID. Whenever
we create Faculty Codes, an entry needs to be added in this table. Validations can
| also be made from the same table. Onclicking the Faculty Codes Un Used Number, | Drill | prithivi & Prakash |  |  |  | 24
we are opening a detail page, where we are currently showing the codes, who used
the code, time generated etc., In addition to that we need to show the Information
Grouped by the Batch ID. Eg., First line will be the Faculty ID, Next we should show
the Batch ID and the Exam Names Associated to that batch. Below that list of
Students who are coming in that batch. (Same Info which is showed currently). Near
each batch we will have two links, which tells to disable the unused faculty codes /
enable the unused codes, which will change the active flag of the unused codes
accordingly
6 | Configurations we need to be make it as exam specific. Currently we are having only
| one configurations common to all exams we need to store the exam ID in sno in that | Drill | Prakash |  |  |  | 24
Configurations table. Need to find the places where we use configuration table and
add exam ID in the query. The retry tokens addition any attempt or first attempt and
subtraction, more token added, should be modified according to the exam.
7 | Settings screen: After the choose exam type region, we need to bring another group.
This is for adding more batches to the student. The Screen will show current batch
| and it will display Faculty Name / ID and the Batch ID / Exam the student got enrolled | Drill | Prithivi |  |  |  | 16
to. Below that there will be label Add New batch code and a text box. Student can
add faculty code here. It will do the same opertaions similar to the sign up,
ie.,entering the data to faculty code table, adding data to the user exam mapping
table.
8 | Edit Test. Click the Exam count, the. Section count. Test will be populated. Clicking
of test will load the question number edit page. On click of back, Section box is
| disappearing. Add more question or remove last question and saving should validate | Drill | Prakash |  |  |  | 8
against the number of questions in level. In create test on tab out of level will keep on
append the question text boxes, which should be changed.
9 | Small UI or alignmmet fixes, to make the application consistent. | CMS & Drill