## Daily Status Tracker
Date | Task in Progress | Application | Assigned to | Detailed status | Completion level | Additional information
2016-02-23 | 1. Enhance Level UI Screen in Drill application to accomadate more than two sections in future | Front End Application | Prithivi Raj G | Done a sample UI with Cards, Bootstrap pills, Bootstrap Carousel.Sample App will be shared with Rajesh for review. On further feedback UI design will be improved. | 20% | Please refer this URL for Code Repository https://github.com/PrithiviRajG/TabAndCards
| 2. Replace the menu bar in Back End application with Fixed top navigation bar to enhance the usability. | Back End Application | Prakah | menu tabs are analyzed to group it into drop downs. | 10%
| 3. Pagination in All Category, Question Status, Sub Step Report, User Administration tabs | Back End Application | Prakah | Yet to start
| 4. classification of exam type in Help Configuration tab | Back End Application | Prakah | Code Analysis and Designing part is done, code change is in progress to replace Help Id with Exam Id | 30%
| 4. Analyzing Git Hub tool to use that as code repository in future. | General | Prithivi Raj G | GitHub repository is used to create the sample project. Further the same repository will be changed by more than 1 people to see the functional flow of GitHub | 20% | Please refer this URL for Code Repository https://github.com/PrithiviRajG/TabAndCards
| 5. JDBC connection in Frond end application is moved to property file | Front End Application | Prithivi Raj G | JDBC Connections are frequently changing. Property files will be used to change all the parameters in single place
| 6. All the Credential details are moved to excel sheet | General |  |  |  | Path: \\VASU-1\Share\Admin Docs
| 7. Status Tracker will be maintained in share path to track day to day activities. | General |  |  |  | \\VASU-1\Share\Admin Docs
2016-02-24 | 1. Enhance Level UI Screen in Drill application to accomadate more than two sections in future | Front End Application | Prithivi Raj G | Analyzing the table structure and Business. | 20%
| 2. Replace the menu bar in Back End application with Fixed top navigation bar to enhance the usability. | Back End Application | Prakah | menu tabs are analyzed to group it into drop downs. | 10%
| 3. Pagination in All Category, Question Status, Sub Step Report, User Administration tabs | Back End Application | Prakah
| 4. classification of exam type in Help Configuration tab | Back End Application | Prakah | Code Analysis and Designing part is done, code change is in progress to replace Help Id with Exam Id | 30%