## Daily Status Tracker
Date | Task in Progress | Application | Assigned to | Detailed status | Completion level | Additional information
2016-02-23 | 1. Enhance Level UI Screen in Drill application to accomadate more than two sections in future | Front End Application | Prithivi Raj G | Done a sample UI with Cards, Bootstrap pills, Bootstrap Carousel.Sample App will be shared with Rajesh for review. On further feedback UI design will be improved. | 20% | Please refer this URL for Code Repository https://github.com/PrithiviRajG/TabAndCards
| 2. Replace the menu bar in Back End application with Fixed top navigation bar to enhance the usability. | Back End Application | Prakah | menu tabs are analyzed to group it into drop downs. | 10%
| 3. Pagination in All Category, Question Status, Sub Step Report, User Administration tabs | Back End Application | Prakah | Yet to start
| 4. classification of exam type in Help Configuration tab | Back End Application | Prakah | Code Analysis and Designing part is done, code change is in progress to replace Help Id with Exam Id | 30%
| 4. Analyzing Git Hub tool to use that as code repository in future. | General | Prithivi Raj G | GitHub repository is used to create the sample project. Further the same repository will be changed by more than 1 people to see the functional flow of GitHub | 20% | Please refer this URL for Code Repository https://github.com/PrithiviRajG/TabAndCards
| 5. JDBC connection in Frond end application is moved to property file | Front End Application | Prithivi Raj G | JDBC Connections are frequently changing. Property files will be used to change all the parameters in single place
| 6. All the Credential details are moved to excel sheet | General |  |  |  | Path: \\VASU-1\Share\Admin Docs
| 7. Status Tracker will be maintained in share path to track day to day activities. | General |  |  |  | \\VASU-1\Share\Admin Docs
2016-02-24 | 1. Enhance Level UI Screen in Drill application to accomadate more than two sections in future | Front End Application | Prithivi Raj G | Analyzing the table structure and Business. | 20%
| 2. Replace the menu bar in Back End application with Fixed top navigation bar to enhance the usability. | Back End Application | Prakah | menu tabs are analyzed to group it into drop downs. | 10%
| 3. Pagination in All Category, Question Status, Sub Step Report, User Administration tabs | Back End Application | Prakah | testing the defects
| 4. classification of exam type in Help Configuration tab | Back End Application | Prakah | Code changes on analysis | 50%
5. Discussing with Rajesh on Release 1
2016-02-25 | 1. Pagination and Help Enhancement code change and fix |  | Prakash | Got few defects on fix. Testing with more test cases | 70%
| 2. Analyzing requirements |  | Prithivi Raj G | Analayzed all the requirements and arrived estimation for each requirement.
| 3. Local SQL server set up |  | Prithivi Raj G | Local SQL server is created to improve the data acces speed in local environemtn | 100%
2016-02-25 | 1. Pagination and Help Enhancement code change and fix |  | Prakash | Both devolopment testing completed. Styles and java script functions should be moved to separate file and it's on progress. | 90%
| 2. Analysis on Grid Requirement |  | Prithivi Raj G | Analysis completed. Have to change lots of code as currently we are not using proper Spring MVC pattern. All the code flows related to this requirement will be done in proper MVC flow | 20%
| 3. Spring Uplift and Hibernate implementation |  | Prithivi Raj G | Hibernate implementation is must for faster code development. Hibernate will be implemented without changing any current flow or code. Requirements in future will use Hibernate for data retieval and save operations. | 20%
| 4. Code Refractory |  | Prithivi Raj G | current code is very clumpsy. Clean up works should be done before touching any requirements. This includes moving style sheets and javascript functions to separate files. Scriplet tag is not recommended as it has lots of disadvantages. Further devolopment will not have scriplet tag.